## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | Complexity | In Charge | Status | Update Details
1 | User Login & Authentication | Security / Common | All Users (Admin, Owner, Jockey, Referee) | Provides an API for users to log into the system. Validates credentials and returns a JWT token for secure requests. | Medium | Lê Nguyễn Chánh Nghĩa, Cao Nhật Lâm | Done | Completed Spring Security and JWT configuration.
2 | Manage Users | User Management | Admin | Management screen for all system users. Allows creating, updating, disabling accounts, and assigning roles (Owner, Jockey, Referee). | Complex | Cao Nhật Lâm, Bùi Đức Tài, Đỗ Quốc Huy,Lê Nguyễn Chánh Nghĩa, Võ Thành Đạt | Done
3 | Horse Management (CRUD) | Horse Data | Admin, Horse Owner | Allows adding, editing, and deleting basic horse information (name, breed, age, weight). Includes authorization checks for the Owner. | Medium | Bùi Đức Tài, Đỗ Quốc Huy | Done
4 | Horse Retirement | Horse Data | Admin, Horse Owner | Handles the business logic for retiring a horse, changing its status from active racing to retired, and archiving its history. | Simple | Cao Nhật Lâm, Đỗ Quốc Huy | Done
5 | Jockey Management | Jockey Data | Admin | Manages information and profiles for jockeys. Updates their status and assigns them to upcoming races. | Medium | Bùi Đức Tài | Done
6 | Manage Race & Tournaments | Race Management | Admin | Creates new seasons and races, schedules events, and allocates horses and jockeys to specific races. | Complex | Cao Nhật Lâm, Bùi Đức Tài, Đỗ Quốc Huy,Lê Nguyễn Chánh Nghĩa, Võ Thành Đạt | Done | Resolved the logic to prevent race scheduling conflicts.
7 | View Public Schedules & Results | Public Data | Guest, All Users | Allows guests to view upcoming race schedules and past race results without requiring an account login. | Medium | Cao Nhật Lâm, Bùi Đức Tài, Võ Thành Đạt | Done
8 | Referee Actions | Race Execution | Referee | Dedicated functionality for referees to update match statuses, input final results, and record placements after a race ends. | Complex | Cao Nhật Lâm, Bùi Đức Tài, Đỗ Quốc Huy,Lê Nguyễn Chánh Nghĩa, Võ Thành Đạt | Done
9 | Public Chat | Communication | All Users | A general chat channel that allows users to discuss races and tournaments. | Simple | Cao Nhật Lâm, Đỗ Quốc Huy | Done | May need to consider WebSocket integration in the future for real-time updates.
10 | AI Chatbot Integration | AI Q&A Assistant | Guest, All Users | Provides an AI-powered conversational chatbot to answer questions about horses, jockeys, owners, and tournament rules in English, Vietnamese, Japanese, and Chinese. | Complex | Cao Nhật Lâm, Lê Nguyễn Chánh Nghĩa | Done | Integrated standalone Flask-based chatbot, set UTF-8 pyodbc database rules, and implemented a floating chatbot bubble UI on Frontend.
11 | Spectator Dashboard Charts | Analytics / Visualization | Spectator | Provides interactive SVG/CSS performance charts and historical statistics on the spectator dashboard. | Medium | Cao Nhật Lâm, Đỗ Quốc Huy | Done | Designed responsive SVG bar/line charts and performance summary tables with mobile layout support.
12 | Real-time Livestream Chat | Communication / Live | Spectator, All Users | Supports real-time chat in active race rooms using WebSockets for instantaneous messages. | Complex | Cao Nhật Lâm, Bùi Đức Tài | Done | Replaced legacy polling with backend WebSocket handlers and designed live chat box UI next to stream player.
13 | Server-side Pagination & Searching | Optimization / Performance | Admin, Horse Owner, Jockey, Referee | Implements backend page requests and frontend search input filters for listing users, horses, and races. | Medium | Cao Nhật Lâm, Bùi Đức Tài, Lê Nguyễn Chánh Nghĩa | Done | Optimized database loading times and improved UI usability with server-side pagination controllers.
14 | Stewards' Inquiry & Weight Comparison | Race Integrity | Referee, Admin | Validates jockey weigh-out vs. weigh-in weights and displays a flashing alert banner when there is a stewards' inquiry. | Medium | Cao Nhật Lâm | Done | Implemented frontend alerts and backend validations for weigh-in discrepancies.
15 | Automated Race Cancellation | Business Rule / Automation | System / Admin | Automatically cancels scheduled races that do not meet the minimum horse entries by the registration deadline. | Medium | Cao Nhật Lâm, Đỗ Quốc Huy | Done | Integrated background timer task to check race registrations and auto-expire pending invitations.
16 | Multilingual System | Localization | All Users | Translates the entire frontend interface including dashboards, error messages, and table fields using dictionary keys. | Medium | Lê Nguyễn Chánh Nghĩa, Bùi Đức Tài | Done | Created dictionary.json mapping and configured i18n.ts provider on React frontend.